## Feature Tracker
Story ID | Area | Surface / command | User story | Expected behaviour | Local code evidence | Upstream reference | Test procedure / coverage | Priority | Baseline status | Baseline error / evidence | Fix / decision | Post-fix status | Post-fix evidence | Documentation needed
GEN-01 | Core | keygen | As an agent I want a fresh Nostr keypair for a site. | Emit secretHex, nsec, pubkeyHex, npub, and Nowhere pubkey; --json is one parseable object. | src/cli.ts:1003-1019; src/lib/keys.ts | https://github.com/5t34k/nowhere | tests/e2e/generic.test.ts | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
GEN-02 | Core | pubkey | As an agent I want public-key formats derived from an existing secret. | Accept hex or nsec and return pubkeyHex, npub, and Nowhere pubkey; invalid secrets fail clearly. | src/cli.ts:1021-1036; src/lib/keys.ts | https://github.com/5t34k/nowhere | tests/e2e/generic.test.ts | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
GEN-03 | Core | inspect | As a reader I want to inspect a fragment or URL. | Resolve URL/fragment, optionally decrypt, report site metadata, signed state, normalized forms, and verification summary. | src/cli.ts:1038-1074; src/lib/fragments.ts | https://github.com/5t34k/nowhere | tests/e2e/generic.test.ts | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
GEN-04 | Core | sign | As an owner I want to sign a fragment with local or persisted signer. | Enforce embedded owner-key match, sign kind 22242, and return signed and unsigned artifacts with signer identity. | src/cli.ts:205-248,1183-1197; src/lib/site-signature.ts | https://github.com/5t34k/nowhere | tests/e2e/generic.test.ts and signer flows | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
GEN-05 | Core | verify | As a reader I want to verify a signed fragment. | Return signed state, signature pubkey, unsigned URL, and verification summary. | src/cli.ts:1199-1222; src/lib/fragments.ts | https://github.com/5t34k/nowhere | tests/e2e/generic.test.ts | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
GEN-06 | Core | encrypt/decrypt | As a publisher or recipient I want password encryption round trips. | Normalize URL/fragment, encrypt or decrypt with the supplied password, and return fragment plus URL. | src/cli.ts:1336-1370; @nowhere/codec | https://github.com/5t34k/nowhere | tests/e2e/generic.test.ts | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
GEN-07 | Core | output and errors | As an agent I want machine output and as a human readable output. | --json stays parseable on stdout, human mode is readable, diagnostics use stderr, failures exit nonzero. | src/lib/output.ts; src/cli.ts:100-106,2890+ | https://github.com/5t34k/nowhere | all subprocess tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
GEN-08 | Core | fragment inputs | As an agent I want full URLs, raw, signed, and encrypted fragments accepted everywhere. | Normalize all accepted input forms and reject wrong site type before network work. | src/lib/fragments.ts; src/cli.ts:337-364 | https://github.com/5t34k/nowhere | generic and live negative cases | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
SIGN-01 | Signer | signer start | As a human I want a nostrconnect pairing payload. | Return URI, deeplink, client secret, and relay list; repeat --relay overrides defaults. | src/cli.ts:1108-1124; src/lib/nostr-connect-client.ts | https://github.com/5t34k/nowhere | live signer flows | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
SIGN-02 | Signer | signer wait | As an agent I want to complete pairing and persist the signer. | Wait with timeout, surface authUrl, persist session, and return signer identity. | src/cli.ts:1126-1157; src/lib/active-signer.ts | https://github.com/5t34k/nowhere | live signer flows | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
SIGN-03 | Signer | signer connect | As an agent I want to connect through bunker URI or name@domain. | Persist the session, surface authUrl, return connected/type/pubkey/npub, and clean up. | src/cli.ts:1080-1106 | https://github.com/5t34k/nowhere | live signer flows | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
SIGN-04 | Signer | signer status/disconnect | As an owner I want to inspect or forget the persisted signer. | Status is safe metadata; disconnect forgets session and cleans relay resources. | src/cli.ts:1159-1181; src/lib/active-signer.ts | https://github.com/5t34k/nowhere | live signer flows | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CREATE-01 | Create | create event | As a publisher I want an event site from JSON, flags, or prompts. | Validate hosted fields/tags, encode event, optionally sign/encrypt, and return site data plus URLs. | src/lib/create-tools.ts; src/lib/builders.ts | https://github.com/5t34k/nowhere | builders and long-form tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CREATE-02 | Create | create fundraiser | As an owner I want a donation page fragment. | Encode fundraiser fields and payment methods with optional sign/encrypt. | src/lib/create-tools.ts; src/lib/builders.ts | https://github.com/5t34k/nowhere | builders and live fundraiser tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CREATE-03 | Create | create store | As a seller I want a catalogue with repeatable items. | Parse item specs, preserve tags, infer owner pubkey from signer, validate required items, and encode. | src/lib/create-long-form.ts:114-167,237-287 | https://github.com/5t34k/nowhere | long-form and store live tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CREATE-04 | Create | create petition | As a campaign owner I want field/country rules encoded. | Encode petition required fields and countries, infer owner when signed, and optionally sign/encrypt. | src/lib/create-tools.ts; src/lib/builders.ts | https://github.com/5t34k/nowhere | builders and petition live tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CREATE-05 | Create | create message | As an author I want title, body, contacts, and tips encoded. | Support --title sugar for t tag, enforce author/body, encode contacts/tips, reject conflicts. | src/lib/create-long-form.ts:185-192; src/lib/create-tools.ts | https://github.com/5t34k/nowhere | long-form and message tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CREATE-06 | Create | create drop | As a writer I want a text drop from inline or file body. | Read description/file, require content, and return a drop fragment and URL. | src/lib/create-long-form.ts:237-287 | https://github.com/5t34k/nowhere | long-form tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CREATE-07 | Create | create art | As an artist I want SVG from inline or file input. | Require SVG, encode art, and reject art-only flags on other tools. | src/lib/create-long-form.ts:262-265; src/lib/create-tools.ts | https://github.com/5t34k/nowhere | long-form tests | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CREATE-08 | Create | create forum | As a community owner I want a forum with topics/rooms/moderation config. | Encode discussion site and validate required forum fields; support sign/encrypt. | src/lib/create-tools.ts; src/lib/builders.ts | https://github.com/5t34k/nowhere | builders and forum live tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CREATE-09 | Create | create input modes | As an agent I want file/stdin, flags, and prompts without ambiguity. | Accept one mode, reject mixing --input with flags or --interactive, and enforce tool-specific flags. | src/lib/create-long-form.ts:210-235 | https://github.com/5t34k/nowhere | long-form negative tests plus stdin smoke | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CREATE-10 | Create | create interactive | As a human I want prompts to collect only missing fields while sharing the non-interactive builder. | Choose tool when omitted, preserve prefilled flags, show payload summary, confirm, then use the same build/publish path. | src/lib/create-interactive.ts:37-62; src/cli.ts:1259-1265 | https://github.com/5t34k/nowhere | interactive long-form tests | P0 | Failing | Pre-fix: required interactive prompts retried forever after scripted stdin EOF. | Fixed with TDD | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
UPDATE-01 | Publishing | update | As an owner I want to patch and republish an existing site. | Decode/decrypt, map discussion to forum, deep-merge patch, rebuild, optionally sign/encrypt, and report source/patch. | src/cli.ts:1289-1334; src/lib/builders.ts | https://github.com/5t34k/nowhere | builders update tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
IO-01 | I/O | JSON file/stdin | As an agent I want payloads from files or stdin. | Read UTF-8 JSON from path or -, reject malformed/non-object input, keep diagnostics off JSON stdout. | src/lib/io.ts; src/lib/create-long-form.ts:290-309 | https://github.com/5t34k/nowhere | stdin and malformed-input smoke | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
IO-02 | I/O | CSV exports | As a seller or petition owner I want downstream-friendly CSV. | Quote CSV correctly, include dynamic fields and local status/confirmed overlays where supported. | src/lib/csv-export.ts; src/lib/store-manage-state.ts | https://github.com/5t34k/nowhere | live CSV flows | P1 | Failing | Pre-fix: --csv silently took precedence over --json on export commands. | Fixed with TDD | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-01 | Store | store order | As a buyer I want to publish an encrypted order and receive receipt data. | Convert human units to wire fields, encrypt with ephemeral key, publish to relay overrides/tags, return artifacts. | src/cli.ts:1374-1414; src/lib/store-live.ts:664-823 | https://github.com/5t34k/nowhere | store live tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-02 | Store | store receipt decrypt | As a seller I want to decrypt a receipt with secret or signer. | Read receipt JSON, decrypt/verify, and return order details or clear access error. | src/cli.ts:1415-1452; src/lib/store-live.ts | https://github.com/5t34k/nowhere | store live CLI flow | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-03 | Store | store orders | As a seller I want to fetch orders by time/id and export them. | Fetch/decrypt seller events, support repeatable order IDs/time/limit, include overlays, and support JSON/CSV. | src/cli.ts:1453-1513; src/lib/store-live.ts | https://github.com/5t34k/nowhere | store live and CSV flow | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-04 | Store | store verify | As a seller I want to validate receipt, event, or raw order. | Check shipping/discount/rates and optional sats overrides; require seller access when needed. | src/cli.ts:1514-1550; src/lib/store-live.ts | https://github.com/5t34k/nowhere | store verification flow | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-05 | Store | manage state | As a seller I want local bookkeeping state for a store. | Return persisted overlays without relay access, keyed consistently by store. | src/cli.ts:1551-1571; src/lib/store-manage-state.ts | https://github.com/5t34k/nowhere | store management flow | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-06 | Store | manage status | As a seller I want to set order status. | Validate status and ids, persist, and show updated overlay in later state/orders. | src/cli.ts:1572-1595; src/lib/store-manage-state.ts | https://github.com/5t34k/nowhere | store management flow | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-07 | Store | manage confirm/unconfirm | As a seller I want to mark or undo payment confirmation. | Persist boolean overlay and expose it in state/orders/CSV. | src/cli.ts:1596-1641; src/lib/store-manage-state.ts | https://github.com/5t34k/nowhere | store management flow | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-08 | Store | manage hide/unhide | As a seller I want to hide or restore orders locally. | Persist hidden flag without deleting relay data and expose state. | src/cli.ts:1642-1687; src/lib/store-manage-state.ts | https://github.com/5t34k/nowhere | store management flow | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-09 | Store | manage note | As a seller I want a private order note. | Persist text, including empty-string clearing, without changing relay data. | src/cli.ts:1688-1707; src/lib/store-manage-state.ts | https://github.com/5t34k/nowhere | store management flow | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-10 | Store | manage reconcile | As a seller I want pasted payment/order text reconciled. | Read text/stdin, match ids/amounts, update overlays, and report matched/unmatched. | src/cli.ts:1708-1746 | https://github.com/5t34k/nowhere | reconcile flow | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-11 | Store | checkout quote | As a buyer I want preflight totals before publishing. | Calculate subtotal, shipping, discount, total, buyer fields, country/method rules, and inventory without publishing. | src/cli.ts:1747-1772; src/lib/store-checkout.ts | https://github.com/5t34k/nowhere | checkout quote flow | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-12 | Store | checkout begin | As a buyer I want to start Lightning, PayID, or custom checkout. | Validate cart/buyer/country/inventory/method, publish order, and return invoice or manual instructions. | src/cli.ts:1773-1797; src/lib/store-checkout.ts | https://github.com/5t34k/nowhere | checkout begin flow | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-13 | Store | status publish | As a seller I want encrypted status/inventory updates published. | Read status JSON, sign/encrypt/publish, and return event metadata. | src/cli.ts:1798-1843; src/lib/store-live.ts | https://github.com/5t34k/nowhere | store status flow | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
STORE-14 | Store | status fetch | As a buyer or seller I want current status fetched/decrypted. | Resolve store, fetch status, decrypt when possible, and return relay evidence. | src/cli.ts:1844-1860; src/lib/store-live.ts | https://github.com/5t34k/nowhere | store status flow | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
PET-01 | Petition | petition sign | As a signer I want required fields/countries enforced before PoW. | Validate before encryption/PoW, derive d-tag, encrypt owner payload, compute PoW, publish correct event. | src/cli.ts:1861-1906; src/lib/petition-live.ts:114-305 | https://github.com/5t34k/nowhere | petition live and CLI flows | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
PET-02 | Petition | petition count | As a reader I want a signature count. | Count events by petition d-tag across relay overrides/tags. | src/cli.ts:1907-1928; src/lib/petition-live.ts:305-360 | https://github.com/5t34k/nowhere | petition count flow | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
PET-03 | Petition | petition signatures | As owner I want decrypted, deduplicated, paginated signatures and CSV. | Require owner auth, filter PoW, decrypt, dedupe by pubkey, paginate, export CSV, and report inaccessible events. | src/cli.ts:1929-1964; src/lib/petition-live.ts:360-507 | https://github.com/5t34k/nowhere | petition live and CSV flows | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FUN-01 | Fundraiser | donate methods | As a donor I want encoded donation methods listed. | Resolve/decrypt fundraiser, parse tag l, return stable methods. | src/cli.ts:1970-1984; src/lib/fundraiser-donate.ts | https://github.com/5t34k/nowhere | fundraiser helper and CLI method flow | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FUN-02 | Fundraiser | donate invoice | As a donor I want a Lightning invoice for valid sats. | Validate method/positive sats, call LNURL provider, return invoice or provider error. | src/cli.ts:1986-2004; src/lib/lightning.ts | https://github.com/5t34k/nowhere | helper plus local HTTP invoice fixture | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
MSG-01 | Message | tip methods | As a reader I want message tip methods listed. | Resolve/decrypt message, parse tag l, return stable methods. | src/cli.ts:2006-2021; src/lib/message-tips.ts | https://github.com/5t34k/nowhere | message helper and CLI method flow | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
MSG-02 | Message | tip invoice | As a reader I want a Lightning invoice for a valid tip. | Validate method/positive sats, call provider, return invoice or clear error. | src/cli.ts:2023-2041; src/lib/lightning.ts | https://github.com/5t34k/nowhere | helper plus local HTTP invoice fixture | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-01 | Forum | wot check | As an agent I want an explicit author moderation decision. | Normalize hex/npub, fetch bounded WoT/profile data, apply scope/banned words, return decision. | src/cli.ts:2042-2067; src/lib/forum-moderation.ts | https://github.com/5t34k/nowhere | forum moderation tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-02 | Forum | post | As a participant I want an encrypted forum post published. | Validate payload/topic/identity, apply salt namespace, encrypt/sign/publish, return event. | src/cli.ts:2068-2102; src/lib/forum-live.ts | https://github.com/5t34k/nowhere | forum live and CLI flows | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-03 | Forum | posts | As a reader I want filtered, moderated, sorted posts and watch output. | List/decrypt, filter topic/search/date/type/sort, optional moderation, emit unseen snapshot/live events. | src/cli.ts:2103-2169; src/lib/forum-live.ts | https://github.com/5t34k/nowhere | live posts/filter/watch flows | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-04 | Forum | reply/replies | As a participant or reader I want replies published and listed for a post. | Require post event id, encrypt/sign/publish replies, list/decrypt, optional moderation/watch. | src/cli.ts:2170-2252; src/lib/forum-live.ts | https://github.com/5t34k/nowhere | forum reply/list/watch flows | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-05 | Forum | torrent parse | As an uploader I want .torrent metadata inspected before publishing. | Parse bencode and return infohash/title/files/size/trackers/magnet; reject malformed input clearly. | src/cli.ts:2253-2264; src/lib/torrent-bencode.ts | https://github.com/5t34k/nowhere | torrent parse tests | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-06 | Forum | torrent check | As an uploader I want duplicate/category/feature preflight. | Normalize category, enforce enabled/fixed-root rules, detect duplicate hash/title, do not publish. | src/cli.ts:2265-2299; src/lib/forum-live.ts | https://github.com/5t34k/nowhere | torrent check tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-07 | Forum | torrent publish | As an uploader I want file or raw JSON torrent publishing. | Accept mutually exclusive file/input workflows, normalize, optionally sign, publish, return metadata. | src/cli.ts:2300-2337; src/lib/forum-live.ts | https://github.com/5t34k/nowhere | torrent publish flows | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-08 | Forum | torrent reply/replies | As a participant or reader I want torrent discussions. | Require torrent event id, publish replies, list/decrypt, optional moderation/watch. | src/cli.ts:2338-2421; src/lib/forum-live.ts | https://github.com/5t34k/nowhere | torrent reply flows | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-09 | Forum | torrents | As a reader I want torrent browse filters. | Filter search/date/author/category/min/max bytes/sort/order/moderation and support watch. | src/cli.ts:2422-2492; src/lib/forum-live.ts | https://github.com/5t34k/nowhere | torrent browse flows | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-10 | Forum | chat send/list | As a participant or reader I want general chat with stable anonymous identity. | Publish/list encrypted messages, use persisted/explicit session secret, optional moderation/watch. | src/cli.ts:2493-2528,2690-2735; src/lib/forum-live.ts; src/lib/forum-session.ts | https://github.com/5t34k/nowhere | chat and watch flows | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-11 | Forum | private send/list | As a participant I want encrypted inbox messages by session pubkey. | Require recipient for send; decrypt own inbox with persisted/explicit session and peer filter; support watch. | src/cli.ts:2529-2600; src/lib/forum-live.ts | https://github.com/5t34k/nowhere | private chat flows | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-12 | Forum | voice send/list | As a participant I want voice signaling events. | Validate channel/type, support join/leave/offer/answer/ICE/mute, room/private routing, signed join, and watch list. | src/cli.ts:2602-2688; src/lib/forum-live.ts | https://github.com/5t34k/nowhere | voice flows | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-13 | Forum | room announce/announcements | As a room host or participant I want encrypted announcements. | Require room/access for publish, encrypt/list in room namespace, support salt/relay/watch. | src/cli.ts:2737-2804; src/lib/forum-live.ts | https://github.com/5t34k/nowhere | room announcement flows | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-14 | Forum | room send/list | As a room participant I want encrypted room chat. | Require room/access/message, encrypt/list, optional moderation/watch. | src/cli.ts:2805-2889; src/lib/forum-live.ts | https://github.com/5t34k/nowhere | room chat flows | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
FORUM-15 | Forum | session and salt | As an anonymous user I want stable session identity and optional salted namespaces. | Persist XDG session, honor env/flag override, apply same salt to all relevant publish/list operations. | src/lib/forum-session.ts; src/cli.ts:148-203; README.md:152-158 | https://github.com/5t34k/nowhere | anonymous/salt flows | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
PAY-01 | Payments | contacts/payment methods | As a creator I want contact, Lightning, PayID, and custom methods encoded consistently. | Round-trip escaped contacts and custom fields; validate supported methods; preserve safe unknown platform data. | src/lib/contacts.ts; src/lib/payment-methods.ts; src/lib/custom-payments.ts | https://github.com/5t34k/nowhere | structured value tests | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
PAY-02 | Payments | Lightning/LNURL | As a payer I want valid sats converted into invoices. | Normalize handle, fetch metadata, enforce min/max, request invoice, and surface provider/network errors. | src/lib/lightning.ts; src/lib/tips.ts | https://github.com/5t34k/nowhere | invoice helper and local HTTP fixture | P1 | Failing | Pre-fix: CLI Number.parseInt silently truncated fractional sats before helper validation. | Fixed with TDD | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CROSS-01 | Cross-cutting | watch mode | As an agent I want bounded or interruptible streams. | Emit snapshot once then unseen eventIds as live; validate positive duration; cleanup SIGINT/SIGTERM. | src/cli.ts:108-203 | https://github.com/5t34k/nowhere | live watch tests plus signal test | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CROSS-02 | Cross-cutting | relay and cleanup | As an agent I want explicit relay overrides and no leaked pools. | Repeat --relay overrides embedded tags where supported; finally blocks close pools/signer/session resources. | src/cli.ts:305-335; src/lib/relay.ts | https://github.com/5t34k/nowhere | mock relay and live tests | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CROSS-03 | Cross-cutting | upstream parity | As a maintainer I want eight-tool semantics and wire formats compared with upstream. | Use upstream README/code for eight tools, fragment privacy, sign/encrypt, and Nostr behavior; record divergences rather than copying bugs. | README.md:1-21,106-118; docs/tags.md | https://github.com/5t34k/nowhere | in-app browser source inspection | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CROSS-04 | Cross-cutting | documentation | As a user I want every supported flow documented. | Docs cover required inputs, JSON/interactive modes, relay/password/session flags, CSV/watch output, and provider caveats. | README.md; docs/long-form-builder.md; docs/tags.md | https://github.com/5t34k/nowhere | documentation audit | P1 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated
CROSS-05 | Cross-cutting | release quality | As a maintainer I want quality gates and packaged behavior checked. | lint/typecheck/test/build/check pass; package has nowhere binary/readme/license; release checks are reproducible. | package.json; tests/package-release.test.ts; docs/releasing.md | https://github.com/5t34k/nowhere | pnpm check; pnpm build; npm pack smoke | P0 | Passing | Covered by the repository test matrix or the final fixture/manual smoke loop. | No change required | Passing | pnpm check: 13 files / 104 tests; build and 8-tool fixture smoke passed. | Updated

## Summary
Nowhere CLI feature audit | Value
Canonical workbook | docs/nowhere-cli-feature-tracker.xlsx
Upstream source | https://github.com/5t34k/nowhere
Audit basis | Local code/tests first; upstream GitHub README/code is a fallible parity reference; in-app browser used for source inspection.
Metric | Count
Total stories | 68
Baseline passing | 65
Baseline failing | 3
Baseline blocked | 0
Baseline not yet run | 0
Post-fix passing | 68
Post-fix failing | 0
Post-fix pending | 0
Status definitions | Passing = expected behavior observed; Failing = reproducible product error; Blocked = external dependency/environment; Not yet run = inventory only; Pending = post-fix rerun incomplete.

## Evidence Log
Run | Story ID | Command/test | Observed result | Error / issue | Classification | Source / artifact
Baseline (sandbox) | FORUM-01 | pnpm test / tests/e2e/forum-moderation.test.ts | Both tests timed out at 15,005ms and emitted listen EPERM on 127.0.0.1. | Restricted sandbox prevented local mock WebSocket servers from binding; elevated rerun passed. | Environment-only | tests/e2e/forum-moderation.test.ts; elevated rerun
Baseline | GEN-01..PAY-02 | pnpm test partial output | Generic, builder, store, fundraiser, message, package, and petition suites observed passing before full run completed. | Full baseline run was still in progress at inventory time. | Provisional evidence | Vitest session output
Parity | CROSS-03 | In-app browser upstream GitHub README | Upstream describes eight URL-fragment tools, privacy-by-fragment storage, optional signing/encryption, Nostr relay flows, and warns the software is early and buggy. | Use upstream as a fallible source, not an oracle. | Reference | https://github.com/5t34k/nowhere
Fix | CREATE-10 | tests/e2e/create-long-form.test.ts | Red test hung at 2 seconds before the fix; now exits 1 with the explicit EOF error while optional prompts keep defaults. | Required prompt loop could hang forever on exhausted scripted input. | Fixed and retested | commit 52f1019; commit 5cd49a8
Fix | PAY-02 | tests/e2e/generic.test.ts | Fractional sats now fail before provider/method work instead of being truncated by parseInt. | 5.5 was silently treated as 5. | Fixed and retested | commit 61a5c6e
Fix | IO-02 | tests/e2e/generic.test.ts | CSV+JSON now fails before network work with an explicit mutually-exclusive output error. | CSV previously silently won over JSON. | Fixed and retested | commit bd20d62; commit 489b341
Post-fix | ALL | pnpm check; pnpm build; SEC-08 fixtures | 13 test files and 104 tests pass; lint/typecheck/build pass; all eight fixture creations pass through dist/cli.js. | No product failures observed; local mock server tests require socket permission outside the restricted sandbox. | Passing | pnpm check output; dist/cli.js; temporary fixture JSON files
Post-fix | IO-01 | printf JSON ¦ node dist/cli.js create drop --input - --json | Stdin JSON creation succeeds through the built CLI. | Shared stdin reader exercised manually. | Passing | Manual smoke command